## Slide 1
2019
2019
Today
August
1 day
8/6/2019
Understanding The Goal
3 days
8/7/2019
Gather Existing Knowledge, Expose Assumptions and Unknowns.
8/9/2019
1 day
8/9/2019
Illuminate all Paths and find who the Safe Driver Product is For.
1 day
8/12/2019
Plan The Very First Prototype Using all The Info Gathered.
1 day
8/14/2019
Build The Very First Prototype To Do The Very Basic Function It Needs To Do.
4 days
8/16/2019
Begin Testing, Gather Data, Record Everything.
8/19/2019
1 day
8/19/2019
Run a real time trial with unsuspecting Driver (Record Footage)
3 days
8/21/2019
Review Data Gathered From Testing and Plan a Second Version of The Prototype
8/23/2019
3 days
8/23/2019
Create Presentation and include Video Footage of the first test, and all data recorded including timeline, models, etc.
8/23/2019